## JIRA (4)
Issue key | Summary | Status | BugType | Comments | Latest
TWO-21033 | JD_UAT_Purchasing org is not populating for a line added on External change order | Rejected |  | SetUp Issue | 23rdJune Tag removed
TWO-20921 | Approval flow on Change order is different | Rejected |  | No Clarity on expected behaviour, follow up mails were sent, no response
P2P-22391 | ChangeRequest: Supplier unable to submit Change Request, getting mandatory fields missing pop-up, even though all fields have value | Rejected |  | SetUp Issue
TWO-20726 | Approved status order is showing at supplier side | Resolved |  | Data issue, have changed the value to IsSupplierVisible =0 and have asked for re-indexing
TWO-21127 | JD_UAT_Estimated delivery date is mandatory on orders at Supplier side but not on Buyer side | In Progress | Legacy | Awaiting response from QA and Avishek
TWO-19491 | Need to get invalid code combination error when we edit the accounting from approver end & then try to approve if the edited accounting in not a valid code combination | In Progress | Legacy | This is a big code change which will require huge Dev and QA efforts.This woul require regression testing
P2P-23119 | Order is not getting created from 'Quick Shop' | In Progress | Regression | 1.0 Issue, Jeetendra is looking into this
P2P-23019 | In Prudential Prod stg, We are allowed to create Adhoc order for partially created order | In Progress | Legacy | 1.0 Amarnath is looking into the issue
P2P-22939 | Prudential: Unable to send Release Order for approval. (Not able to add adhoc approver in Orders) | In Progress | Configuration | Chnages in setting value script share with Abhijit by Chetan | Status changed to ReadyForTesting
P2P-22880 | Track status issue | In Progress |  | This is happening only for Automation, manually working fine
CLI-84696 | Page not found while navigating from order to landing page | In Progress | Bug-Functional Bug | Revathi working on the issue
CLI-84689 | Change request submitted by supplier not showing buyer Task menu | In Progress |  | The issue is there in Production also, this is not implemented
TWO-21091 | Document is going to "Sending To Supplier Failed" when flipped from catalog to PO with different suppliers | Reopened |  | The document is reprocessed, QA to take action on this
P2P-23124 | In Prudential-UAT, unable to perform any action on order | Reopened |  | Specific to IE version, Fanisha working on this
CLI-84651 | Not able to download Order print. getting loading icon. | Reopened | Bug-Functional Bug | Aspose Dll Issue, the issue is there in production also, this requires node restart
TWO-20314 | "Submitted On" and "Submitted by" is not getting displayed for Orders, Receipt and Invoices in track status | Draft | Legacy | The issue is there in Production also, this is not implemented, this is a big code change and will require lot of regression
P2P-23136 | In Prudential-UAT, added approvers are getting deleted on Order | Draft |  | 1.0 Fanisha is working on the issue
P2P-23134 | On PO Custom attributes are not editable. | Draft |  | 1.0 Fanisha is working on the issue
TWO-21159 | JD_UAT_Server Error when supplier open the order for which change request has been rejected by buyer | In Progress | Legacy | Srikanth- this is a legacy issue where if multiple windows are open, the issue will come